## 00 Project Description
Congratulations—you've landed a job with Funny Money Transfer, whose product is an online payment service for transferring "Funny bucks" between friends. However, they don't have a product yet. You've been tasked with writing an application that includes both a RESTful API server and a client UI.

## 01 Hi Level Architecture
Layer | Client or Server | Notes
Database | Server | See schema image; SQL server
Data Access | Server | EF
API | Server | Web API
Services | Client | RestSharp
UI | Client | WPF? Web?

## 02 Project Plan
# | Use Case | Details | Notes | Complete? | Commit
0 | Create database | 1. Create database 2. Create tables and relationships 3. Initialize data 4. Script it out | Script to create database and tables, and initialize data for the transfer types and transfer statuses is complete; some deviations from the db specs which are detailed in 04 DB Schema | YES | N/A
1 | Create and configure data access layer | 1. Create DAL project 2. Reverse engineer model classes and db context from database 3. Configure and fine tune the model classes and db context 4. Move conn string into config | https://learn.microsoft.com/en-us/ef/core/managing-schemas/scaffolding/?tabs=dotnet-core-cli My customizations are in FunnyMoneyTransferContext.cs::OnModelCreatingPartial() | YES | 2f8f108 cc9147f
2 | As a user of the system, I need to be able to register myself with a username and password. | 1. A new registered user starts with an initial balance of 1,000 TE Bucks. 2. The ability to register has been provided in your starter code.
3 | As a user of the system, I need to be able to log in using my registered username and password. | 1. Logging in returns an Authentication Token. I need to include this token with all my subsequent interactions with the system outside of registering and logging in. 2. The ability to log in has been provided in your starter code.
4 | As an authenticated user of the system, I need to be able to see my Account Balance.
5 | As an authenticated user of the system, I need to be able to *send* a transfer of a specific amount of TE Bucks to a registered user. | 1. I should be able to choose from a list of users to send TE Bucks to. 2. A transfer includes the User IDs of the from and to users and the amount of TE Bucks. 3. The receiver's account balance is increased by the amount of the transfer. 4. The sender's account balance is decreased by the amount of the transfer. 5. I can't send more TE Bucks than I have in my account. 6. A Sending Transfer has an initial status of "approve."
6 | As an authenticated user of the system, I need to be able to see transfers I have sent or received.
7 | As an authenticated user of the system, I need to be able to retrieve the details of any transfer based upon the transfer ID.
8 | As an authenticated user of the system, I need to be able to *request* a transfer of a specific amount of TE Bucks from another registered user. | 1. I should be able to choose from a list of users to request TE Bucks from. 2. A transfer includes the User IDs of the from and to users and the amount of TE Bucks. 3. A Request Transfer has an initial status of "pending." 4. No account balance changes until the request is approved. 5. The transfer request should appear in both users' list of transfers (use case #5).
9 | As an authenticated user of the system, I need to be able to see my "pending" transfers.
10 | As an authenticated user of the system, I need to be able to either approve or reject a Request Transfer. | 1. I can't "approve" a given Request Transfer for more TE Bucks than I have in my account. 2. The Request Transfer status is "approved" if I approve, or "rejected" if I reject the request. 3. If the transfer is approved, the requester's account balance is increased by the amount of the request. 4. If the transfer is approved, the requestee's account balance is decreased by the amount of the request. 5. If the transfer is rejected, no account balance changes.

## 03 Sample Screens
## Sample screens ### Use Case 3 - Current balance ``` Your current account balance is: $9999.99 ``` ### Use Case 4 - Send TE Bucks ``` ------------------------------------------- Users ID Name ------------------------------------------- 313 Bernice 54 Larry --------- Enter ID of user you are sending to (0 to cancel): Enter amount: ``` ### Use Case 5 - View transfers ``` ------------------------------------------- Transfers ID From/To Amount ------------------------------------------- 23 From: Bernice $ 903.14 79 To: Larry $ 12.55 --------- Please enter transfer ID to view details (0 to cancel): " ``` ### Use Case 6 - Transfer details ``` -------------------------------------------- Transfer Details -------------------------------------------- Id: 23 From: Bernice To: Me Myselfandi Type: Send Status: Approved Amount: $903.14 ``` ### Use Case 7 - Requesting TE Bucks ``` ------------------------------------------- Users ID Name ------------------------------------------- 313 Bernice 54 Larry --------- Enter ID of user you are requesting from (0 to cancel): Enter amount: ``` ### Use Case 8 - Pending requests ``` ------------------------------------------- Pending Transfers ID To Amount ------------------------------------------- 88 Bernice $ 142.56 147 Larry $ 10.17 --------- Please enter transfer ID to approve/reject (0 to cancel): " ``` ### Use Case 9 - Approve or reject pending transfer ``` 1: Approve 2: Reject 0: Don't approve or reject --------- Please choose an option: ```

## 04 DB Schema
## Database Schema ![Database schema](./img/database_schema.png) ### Users table The `users` table stores the login information for users of the system. ¦ Field ¦ Description ¦ ¦ --------------- ¦ ------------------------------------------------------------------------------ ¦ ¦ `user_id` ¦ Unique identifier of the user ¦ ¦ `username` ¦ String that identifies the name of the user; used as part of the login process ¦ ¦ `password_hash` ¦ Hashed version of the user's password ¦ ¦ `salt` ¦ String that helps hash the password ¦ ### Accounts table The `accounts` table stores the accounts of users in the system. ¦ Field ¦ Description ¦ ¦ --------------- ¦ ------------------------------------------------------------------ ¦ ¦ `account_id` ¦ Unique identifier of the account ¦ ¦ `user_id` ¦ Foreign key to the `users` table; identifies user who owns account ¦ ¦ `balance` ¦ The amount of TE bucks currently in the account ¦ ### Transfer types table The `transfer_types` table stores the types of transfers that are possible. ¦ Field ¦ Description ¦ ¦ -------------------- ¦ --------------------------------------- ¦ ¦ `transfer_type_id` ¦ Unique identifier of the transfer type ¦ ¦ `transfer_type_desc` ¦ String description of the transfer type ¦ There are two types of transfers: ¦ `transfer_type_id` ¦ `transfer_type_desc` ¦ Purpose ¦ ¦ ------------------ ¦ -------------------- ¦ ---------------------------------------------------------------------- ¦ ¦ 1 ¦ Request ¦ Identifies transfer where a user requests money from another user ¦ ¦ 2 ¦ Send ¦ Identifies transfer where a user sends money to another user ¦ ### Transfer statuses table The `transfer_statuses` table stores the statuses of transfers that are possible. ¦ Field ¦ Description ¦ ¦ ---------------------- ¦ ----------------------------------------- ¦ ¦ `transfer_status_id` ¦ Unique identifier of the transfer status ¦ ¦ `transfer_status_desc` ¦ String description of the transfer status ¦ There are three statuses of transfers: ¦ `transfer_status_id` ¦ `transfer_status_desc` ¦Purpose ¦ ¦ -------------------- ¦ -------------------- ¦ --------------------------------------------------------------------------------------- ¦ ¦ 1 ¦ Pending ¦ Identifies transfer that hasn't occurred yet and requires approval from the other user ¦ ¦ 2 ¦ Approved ¦ Identifies transfer that has been approved and occurred ¦ ¦ 3 ¦ Rejected ¦ Identifies transfer that wasn't approved ¦ ### Transfers table The `transfer` table stores the transfers of TE bucks. ¦ Field ¦ Description ¦ ¦ -------------------- ¦ ----------------------------------------------------------------------------------------------- ¦ ¦ `transfer_id` ¦ Unique identifier of the transfer ¦ ¦ `transfer_type_id` ¦ Foreign key to the `transfer_types` table; identifies type of transfer ¦ ¦ `transfer_status_id` ¦ Foreign key to the `transfer_statuses` table; identifies status of transfer ¦ ¦ `account_from` ¦ Foreign key to the `accounts` table; identifies the account that the funds are being taken from ¦ ¦ `account_to` ¦ Foreign key to the `accounts` table; identifies the account that the funds are going to ¦ ¦ `amount` ¦ Amount of the transfer
I am using a Starting Balances table that will contain the beginning balance for each account
An account's balance is therefore the sum of starting balance, transfers out, and transfers in
As such…balance doesn't need to be stored in the accounts table
The accounts-to-starting balances relationship is one to one
I also made the decision not to have cascading updates and deletes in the db, a decision that may need to be revisited
And I enforced a relationship in my db differently than indicated here; accounts-to-users is one to one instead of many to one
(Allowing multiple accounts per user could be a new feature down the road; I added this to 99 TODO)
Lastly - I added a date created column to the accounts, users, transfers, and starting balances tables

## 05 Business Rules
# | Layer | Rule | Enforced by
1 | Database | Transfer type descriptions must be unique in the transfer_types table | unique constraint on this column
2 | Database | Transfer status descriptions must be unique in the transfer_statuses table | unique constraint on this column
3 | Database | Usernames must be unique in the users table | unique constraint on this column
4 | Database | User ids must be unique in the accounts table, i.e. one user, one account and vice versa | unique constraint on this column
5 | Database | Account ids must be unique in the starting balances table, i.e., one account, one starting balance and vice versa | unique constraint on this column
6 | Database | transfers must have different 'from' and 'to' accounts | check constraint in transfers table
7 | Database | transfer amounts must be greater than zero | check constraint in transfers table

## 99 TODO
1 | Consider allowing a user to have more than one account
2 | First and last names for users